## Hoja1
Story | story point | Iteration | Period | Ideal days | Real days
Compile library for Unity project | 2 | 1 | 03/30 - 04/12 | 10 | 9 | 03/30 - 04/09
Simplify calibration method | 2
Simplify tare and configuration of glove | 5
Simplify Scan glove | 3
Simplify set glove ID to model | 3
Simplify all hand movement | 8 | 2 | 04/13/ - 04/26 |  |  | 04/09 -
Simplify all fingers movement | 8
Simplify finger gestures | 8 | 3 | 04/27 - 05/10
Simplify arms up and down | 8
simplify arm front and back | 8 | 4 | 05/11 - 05/24
Simplify pick up movement | 8
Simplify push movement | 8 | 5 | 05/25 - 06/07
Attach hands to camera view | 5
Make test app | 13 | 6 | 06/08/ - 06/21
Resolver conneccion a rifact en pc offcina | 8 | 7

## Hoja2
AddModule | Set ID of module to hand or arm